HealthSync Indonesia

MVP Scope Document

Batasan Fitur Rilis Tahap Pertama

Versi 1.0 | 14 September 2026

Kategori: Bisnis & Produk

# 1. MVP Definition

MVP (Minimum Viable Product) HealthSync v1.0 adalah rilis pertama yang memvalidasi core value proposition: real-time health monitoring dengan emergency response terintegrasi, dalam skala pilot 2 Rumah Sakit.

# 2. IN SCOPE (MVP)

✅ Multi-role authentication (Pasien, Dokter, RS, Apotek, Driver)

✅ Symptom checker (rule-based decision tree, bukan AI/ML)

✅ Konsultasi chat text-based (video di Phase 2)

✅ e-Prescription + apotek fulfillment + delivery tracking

✅ Smartwatch pairing & data ingestion (1 merk: Samsung Galaxy Watch)

✅ Alert system (threshold-based, 3 level escalation)

✅ Command Center dashboard (real-time monitoring, read + basic action)

✅ Rujukan digital (form + status tracking + matching dasar)

✅ Ambulance dispatch (manual assign oleh Command Center)

✅ RS recommendation (distance-based + kapasitas)

✅ Notifikasi (Push + SMS untuk critical)

# 3. OUT OF SCOPE (Phase 2+)

❌ AI/ML untuk diagnosis atau predictive analytics

❌ Video consultation (Phase 2)

❌ Integrasi BPJS Kesehatan (Phase 2)

❌ SATUSEHAT full integration (MVP: manual export FHIR)

❌ Multi-smartwatch support (Phase 2)

❌ Auto-dispatch ambulance tanpa konfirmasi (Phase 2)

❌ Payment gateway terintegrasi (MVP: manual transfer)

❌ Multi-language support

❌ Telemedicine spesialis langka

❌ White-label untuk RS partner

# 4. MVP Success Criteria

| Metric | Target | Timeline |
| --- | --- | --- |
| Pilot di 2 RS partner | Go-live | Bulan 9 |
| Pasien aktif monitoring | 100 pasien | 3 bulan post-launch |
| Alert response time < 3 menit | 95% compliance | Bulan 1 post-launch |
| System uptime | > 99.5% | Bulan 1 post-launch |
| NPS pasien | > 40 | Bulan 3 post-launch |
| Zero critical security incidents | 0 incidents | Ongoing |

# 5. Tech Debt Accepted in MVP

| Item | Alasan | Plan untuk Fix |
| --- | --- | --- |
| Hardcoded threshold values | Kecepatan development | Phase 2: configurable per pasien |
| Single smartwatch brand | Fokus integrasi | Phase 2: abstraction layer |
| Manual ambulance dispatch | Validasi flow dulu | Phase 2: auto-dispatch |
| No offline mode Command Center | Complexity tinggi | Phase 2: PWA + service worker |
| No video consultation | Infrastruktur berat | Phase 2: WebRTC / Agora |

# 6. MVP Timeline

| Sprint | Durasi | Fokus | Deliverable |
| --- | --- | --- | --- |
| Sprint 1-2 | Bulan 1 | Foundation | Auth, Profile, Infra Setup, CI/CD |
| Sprint 3-4 | Bulan 2 | Patient Portal | Symptom Checker, Chat Konsultasi |
| Sprint 5-6 | Bulan 3 | IoT Pipeline | Smartwatch Integration, Alert System |
| Sprint 7-8 | Bulan 4 | Command Center | Dashboard, e-Prescription, Apotek |
| Sprint 9 | Bulan 5 | Integration | Rujukan, Ambulance, E2E Testing |
| Sprint 10 | Bulan 5-6 | Hardening | Security audit, UAT, Bug fixing |
| Pilot Launch | Bulan 6 | Go-Live | Deploy ke 2 RS pilot |